## Sheet1
P06F24 | Team Members | Project Start Date
SkillScope | Ali Salman (Team Lead) | 2024-11-14
Hasnain Hafeez ( Member )
Syed Rizwan Hussain (Member )
| Hasan Ali Zain ( Member ) | [5 empty] | 2024-11-14 | [6 empty] | 2024-11-21 | [6 empty] | 2024-11-28 | [6 empty] | 2024-12-05 | [6 empty] | 2024-12-12 | [6 empty] | 2024-12-19 | [6 empty] | 2024-12-26 | [6 empty] | 2025-01-02 | [6 empty] | 2025-01-09 | [6 empty] | 2025-01-16 | [6 empty] | 2025-01-23 | [6 empty] | 2025-01-30 | [6 empty] | 2025-02-06 | [6 empty] | 2025-02-13 | [6 empty] | 2025-02-20 | [6 empty] | 2025-02-27 | [6 empty] | 2025-03-06 | [6 empty] | 2025-03-13 | [6 empty] | 2025-03-20 | [6 empty] | 2025-03-27 | [6 empty] | 2025-04-03 | [6 empty] | 2025-04-10 | [6 empty] | 2025-04-17 | [6 empty] | 2025-04-24 | [6 empty] | 2025-05-01 | [6 empty] | 2025-05-08 | [6 empty] | 2025-05-15 | [6 empty] | 2025-05-22 | [6 empty] | 2025-05-29 | [6 empty] | 2025-06-05 | [6 empty] | 2025-06-12 | [6 empty] | 2025-06-19 | [6 empty] | 2025-06-26 | [6 empty] | 2025-07-03
 | time axis 2024-11-14 to 2025-07-09
Task | Subtask | Assigned to | Start | Days | End | Done % | time axis 2024-11-14 to 2025-07-09
FYP 1 (DAYS 1-120)
1. App and Website Design(Days 60) | 1.1 Overview and Landing page | All Members | 2024-11-14 | 3 Days | 2024-11-16 | 1%
| 1.2 Landing Page Wireframe | Hasan , Ali | 2024-11-17 | 1 Day | 2024-11-18 | 2%
| 1.3 Implement Branding and Colors | Rizwan,Hasnain | 2024-11-18 | 1 Day | 2024-11-19 | 3%
| 1.4 Add animation and transitions | Hasan | 2024-11-19 | 1 Day | 2024-11-20 | 4%
| 1.5 Setup navigation links | Hasan | 2024-11-21 | 2 Days | 2024-11-22 | 5%
| 1.6 User Authentication (Login/Signup) | Hasan,Ali | 2024-11-22 | 3 Days | 2024-11-25 | 6%
| 1.7 Design Login Page UI | Hasnain,Rizwan | 2024-11-26 | 1 Day | 2024-11-27 | 7%
| 1.8 Design Signup Page UI | Hasnain | 2024-11-27 | 1 Day | 2024-11-28 | 8%
| 1.9 Add forms fields and validation | Rizwan | 2024-11-29 | 2 Days | 2024-12-01 | 9%
| 1.10 Implement Error messages | Rizwan , Hasan | 2024-12-01 | 2 Days | 2024-12-03 | 10%
| 2.0 Survey Form Interface | Ali | 2024-12-03 | 2 Days | 2024-12-05 | 12%
| 2.1 Design form layout | Ali,Hasan | 2024-12-05 | 2 Days | 2024-12-07 | 13%
| 2.2 Add skills and experience fields | Ali | 2024-12-07 | 2 Days | 2024-12-09 | 14%
| 2.3 Integrate validation checks | Hasnain,Ali | 2024-12-09 | 1 Days | 2024-12-10 | 14%
| 2.4 Implement form submission | Rizwan | 2024-12-10 | 3 Days | 2024-12-13 | 15%
| 2.5 Dashboard Layout for new and returning users | All Members | 2024-12-13 | 3 Days | 2024-12-16 | 15%
| 2.6 Design dashboard layout for new users | All Members | 2024-12-16 | 2 Days | 2024-12-18 | 17%
| 2.7 Design dashboard layout for returning users | All Members | 2024-12-18 | 3 Days | 2024-12-21 | 19%
| 2.8 Create start analysis button for new users | Ali | 2024-12-21 | 1 Days | 2024-12-22 | 19%
| 2.9 Setup Display for past analysis | Hasan,Ali,Rizwan | 2024-12-22 | 3 Days | 2024-12-25 | 21%
| 2.10 Graphical Data Representation | Hasan,Ali,Rizwan | 2024-12-26 | 4 Days | 2024-12-30 | 24%
| 3.0 Design job market trends graph | All Members | 2024-12-30 | 1 Days | 2025-01-01 | 25%
| 3.1 create past analysis results graph | Hasnain | 2025-01-01 | 3 Days | 2025-01-03 | 25%
| 3.2 Add top fields in market graph | Hasan,Hasnain | 2025-01-03 | 4 Days | 2025-01-07 | 26%
| 3.3 Implement comparison chart for fields | Hasan,Hasnain | 2025-01-06 | 3 Days | 2025-02-08 | 27%
| 3.4 Choose field page | Ali | 2025-01-08 | 2 Days | 2025-01-10 | 28%
| 3.5 Top Tech stacks suggestions page | Rizwan,Ali | 2025-01-10 | 2 Days | 2025-01-12 | 28%
| 3.6 Job role cards page | Hasan | 2025-01-12 | 2 Days | 2025-01-14 | 29%
| 3.7 Tech combination suggestion page | Hasan,Ali | 2025-01-14 | 2 Days | 2025-01-16 | 29%
30%
30%
30%
30%
30%
2. Database Setup and initial data collection(Days 61-120) | 4.2 Define user schema | All Members | 2025-01-16 | 4 Days | 2025-01-20 | 32%
| 4.3 Setup database tables for job roles | Hasnain | 2025-01-20 | 2 Days | 2025-01-22 | 32%
| 4.4 Create backups | Hasnain,Ali | 2025-01-22 | 2 Days | 2025-01-24 | 35%
| 4.5 Test database connection | Hasnain | 2025-01-24 | 1 Day | 2025-01-25 | 36%
| 4.6 Api Integration for job data collection | All Members | 2025-01-25 | 3 Days | 2025-01-28 | 37%
| 4.7 Schedule Api data fetch | Ali | 2025-01-28 | 3 Days | 2025-01-30 | 38%
| 4.8 Validate and clean collected data | Ali,Rizwan | 2025-02-01 | 2 Days | 2025-02-03 | 39%
| 4.9 Store job market data in database | Ali,Rizwan | 2025-02-03 | 3 Days | 2025-02-06 | 39%
| 4.10 Define schema for market trends | Hasnain | 2025-02-06 | 2 Days | 2025-02-08 | 40%
| 5.1 Test data retrival accuracy | All Members | 2025-02-08 | 2 Days | 2025-02-10 | 42%
| 5.2 Initial Machine learning preparation | Ali,Rizwan | 2025-02-10 | 4 Days | 2025-02-14 | 42%
| 5.3 Gather and clean initial job data | Rizwan | 2025-02-14 | 4 Days | 2025-02-18 | 43%
| 5.4 Organize data for model training | Rizwan | 2025-02-18 | 3 Days | 2025-02-21 | 44%
| 5.5 Create feature extraction pipeline | Rizwan,Ali | 2025-02-21 | 3 Days | 2025-02-24 | 45%
| 5.6 Validate Preprocessed data | Ali | 2025-02-24 | 4 Days | 2025-02-28 | 46%
| 5.7 Feature Engineering | Ali | 2025-03-01 | 2 Days | 2025-03-03 | 47%
| 5.8 Extract features for tech stack recommendation | Ali | 2025-03-03 | 4 Days | 2025-03-07 | 49%
| 5.9 Store Preprocessed data in database | Hasnain | 2025-03-07 | 2 Days | 2025-03-09 | 50%
FYP-2(DAYS 121-240) |  | All Members |  |  |  | 50%
Machine Learning Model Training and development(Days 121-170) | 6.0 Train Initial prediction model | All Members | 2025-03-09 | 3 Days | 2025-03-12 | 51%
| 6.1Train initial tech stack recommendation model | Ali | 2025-03-12 | 3 Days | 2025-03-15 | 52%
| 6.2 Evaluate model performance on test set | Ali,Hasnaim,Hasan | 2025-03-15 | 4 Days | 2025-03-19 | 53%
| 6.3 Tune model hyperparameters | Ali,Hasan | 2025-03-19 | 4 Days | 2025-03-23 | 54%
| 6.4 Model Evaluation and refinement | Ali,Hasnain,Rizwan | 2025-03-23 | 4 Days | 2025-03-27 | 55%
| 6.5 Refine data processing and features | Rizwan | 2025-03-27 | 1 Day | 2025-03-28 | 56%
| 6.6 Retrain model with updated data | Hasnain | 2025-03-28 | 2 Days | 2025-03-30 | 58%
| 6.7 Conduct Validation tests | All Members | 2025-03-30 | 1 Days | 2025-03-31 | 60%
Backend Development(Days 171-200) | 6.8 Develop logic for career field prediction | All Members | 2025-04-01 | 4 Days | 2025-04-04 | 61%
| 6.9 Build tech stack recommendation logic | Hasnain | 2025-04-04 | 3 Days | 2025-04-07 | 64%
| 6.10 Integrate job level suggestion logic | Hasnain | 2025-04-07 | 4 Days | 2025-04-11 | 66%
| 7.1 Dashboard Integration | Hasnain | 2025-04-11 | 4 Days | 2025-04-15 | 67%
| 7.2 link job market trends | Hasnain | 2025-04-15 | 3 Days | 2025-04-18 | 68%
| 7.3 Integrate tech stack suggestions on dashboard | Hasnain,Ali,Hasan | 2025-04-18 | 4 Days | 2025-04-22 | 69%
| 7.4 Test data flow on dashboard | All Members | 2025-04-22 | 3 Days | 2025-04-25 | 75%
Integration and Testing(Days 201-220) | 7.5 Integrate login and signup with backend | Hasnain,Rizwan | 2025-04-25 | 4 Days | 2025-04-29 | 77%
| 7.6 Connecting form with database | Hasnain | 2025-04-29 | 1 Day | 2025-04-30 | 79%
| 7.7 Link prediction and recommendation logic | Ali,Hasnain,Rizwan | 2025-05-01 | 3 Days | 2025-05-05 | 81%
| 7.8 Test overall integration | Hasan,Rizwan | 2025-05-05 | 3 Days | 2025-05-08 | 84%
| 7.9 Functionality Testing | All Members | 2025-05-08 | 2 Days | 2025-05-10 | 86%
Deployment and user feedback collection (Days 221-240) | 8.0 Finalize documentation and codebase | All Members | 2025-05-10 | 4 Days | 2025-05-14 | 90%
| 8.1 Setup Hosting and deployment enviroment | Hasan | 2025-05-14 | 4 Days | 2025-05-18 | 91%
| 8.2 Conduct final test on deployment | Hasnain,Ali,Rizwan | 2025-05-18 | 4 Days | 2025-05-22 | 92%
| 8.3 Platfrom launch and monitoring | All Members | 2025-05-22 | 4 Days | 2025-05-26 | 95%
| 8.4 Monitor for errors | Hasan,Ali,Rizwan | 2025-05-26 | 4 Days | 2025-05-30 | 97%
| 8.5 Gather user feedback and future improvements | All Members | 2025-06-01 | 4 Days | 2025-06-04 | 100%